## Timeline
` |  | Timeline #Phase 1
PROJECT TITLE |  |  |  | Revamps Knowledge Website URL STAGE : https://www.trueplookpanya.com/knowledge2/
PROJECT UPDATE |  |  |  | 2022-11-14
[8 empty] | November | [22 empty] | December
| WBS NUMBER | TASK TITLE | Owner | START DATE (m/d/y) | DUE DATE (m/d/y) | DURATION ( * 25 Days ) | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[8 empty] | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 31
|  | 1. Frontend | [5 empty] | WEEK 1 5: วันคล้ายวันเฉลิมพระชนมพรรษา; WEEK 4 30: วันหยุดชดเชย; WEEK 4 31: วันสิ้นปี
| 1.1 | Home page | Olan | 2022-11-07 | 2022-11-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9
| 1.2 | Blog detail | Olan | 2022-11-14 | 2022-11-15 | 2 | 100% | bar: WEEK 3 14 to WEEK 3 15
| 1.3 | Category level 1 | Olan | 2022-11-10 | 2022-11-11 | 2 | 100% | bar: WEEK 2 10 to WEEK 2 11
| 1.4 | Category level 2 | Olan | 2022-11-10 | 2022-11-11 | 2 | 100% | bar: WEEK 2 10 to WEEK 2 11
| 1.5 | Category level 3 | Olan | 2022-11-09 | 2022-11-10 | 2 | 100% | bar: WEEK 2 9 to WEEK 2 10
| 1.6 | Search Result | Olan | 2022-11-09 | 2022-11-10 | 2 | 100% | bar: WEEK 2 9 to WEEK 2 10
| 1.7 | OG | Olan |  |  | 0 | 100%
| 1.8 | Breadcrumbs | Olan | 2022-11-09 | 2022-11-10 | 2 | 100% | bar: WEEK 2 9 to WEEK 2 10
| 1.9 | Share social | Olan | 2022-11-09 | 2022-11-10 | 2 | 100% | bar: WEEK 2 9 to WEEK 2 10
| 1.10 | Bookmark | Olan | 2022-11-09 | 2022-11-10 | 2 | 100% | bar: WEEK 2 9 to WEEK 2 10
2. API , CMS , Remigration Data
| 2.1 | Prepare data Ads Script, Category, Image Banner, OG, Category for Dev | Jit | 2022-11-14 | 2022-11-14 | 1 | 100% | bar: WEEK 3 14
| 2.2 | Duplicate module knowledge old (PHP) to new module | Jit | 2022-11-15 | 2022-11-18 | 4 | 0% | bar: WEEK 3 15 to WEEK 3 18
| 2.3 | Set .htaccess Redirect URL | Jit+Olan | 2022-11-21 | 2022-11-21 | 1 | 0% | bar: WEEK 4 21
| 2.4 | Dev CMS for select one zone ระบบหลังบ้าน | Na | 2022-11-08 | 2022-11-08 | 1 | 100%
| 2.5 | get data zone | Na | 2022-11-08 | 2022-11-08 | 1 | 100% | bar: WEEK 2 8
| 2.6 | get data category | Na | 2022-11-10 | 2022-11-10 | 1 | 100% | bar: WEEK 2 9 to WEEK 2 10
| 2.7 | get data connent by category level 1 | Na | 2022-11-10 | 2022-11-10 | 1 | 100% | bar: WEEK 2 10
| 2.8 | get data connent by category level 2 | Na | 2022-11-10 | 2022-11-10 | 1 | 100% | bar: WEEK 2 10
| 2.9 | get data connent by category level 3 | Na | 2022-11-14 | 2022-11-14 | 1 | 100% | bar: WEEK 2 11
| 2.10 | get data connent หน้า Home | Na | 2022-11-14 | 2022-11-14 | 1 | 100% | bar: WEEK 3 14
| 2.11 | get data connent function newcontents | Na | 2022-11-14 | 2022-11-14 | 1 | 100% | bar: WEEK 3 14
| 2.12 | get data connent function newcontents list pagaing | Na | 2022-11-14 | 2022-11-14 | 1 | 100% | bar: WEEK 3 14
| 2.13 | get data connent function detail | Na | 2022-11-15 | 2022-11-15 | 1 | 100% | bar: WEEK 3 15
| 2.14 | get data connent function relate by Cateory_id | Na | 2022-11-15 | 2022-11-15 | 1 | 90% | bar: WEEK 3 15
| 2.15 | get data connent function recommended | Na | 2022-11-15 | 2022-11-15 | 1 | 100% | bar: WEEK 3 15
| 2.16 | get data connent function editorpicks | Na | 2022-11-15 | 2022-11-16 | 2 | 90% | bar: WEEK 3 15 to WEEK 3 16
| 2.17 | get data connent function random data | Na | 2022-11-15 | 2022-11-16 | 2 | 80% | bar: WEEK 3 15 to WEEK 3 16
| 2.18 | get data connent function relate by conten id | Na | 2022-11-15 | 2022-11-16 | 2 | 100% | bar: WEEK 3 15 to WEEK 3 16
| 2.19 | access token | Na | 2022-11-07 | 2022-11-07 | 1 | 100% | bar: WEEK 2 7
| 2.20 | check token | Na | 2022-11-07 | 2022-11-07 | 1 | 100% | bar: WEEK 2 7
| 2.21 | validate token | Na | 2022-11-07 | 2022-11-07 | 1 | 100% | bar: WEEK 2 7
| 2.22 | add update and get view | Na | 2022-11-07 | 2022-11-07 | 1 | 100% | bar: WEEK 2 7
| 2.23 | get data tag | Na | 2022-11-07 | 2022-11-07 | 1 | 100% | bar: WEEK 2 7
| 2.24 | subscribers or follow up | Na | 2022-11-09 | 2022-11-09 | 1 | 100% | bar: WEEK 2 9
| 2.25 | favorite | Na | 2022-11-09 | 2022-11-09 | 1 | 100% | bar: WEEK 2 9
| 2.26 | Search result Content | Na | 2022-11-09 | 2022-11-09 | 1 | 100% | bar: WEEK 2 9
| 2.27 | Count read content by user | Na | 2022-11-09 | 2022-11-09 | 1 | 100% | bar: WEEK 2 9
| 2.28 | get data connent function viewfollow | Na | 2022-11-15 | 2022-11-15 | 1 | 100% | bar: WEEK 3 15
| 2.29 | get data connent function detachzone | Na | 2022-11-15 | 2022-11-15 | 1 | 100% | bar: WEEK 3 15
| 2.30 | get data connent function file | Na | 2022-11-14 | 2022-11-14 | 1 | 100% | bar: WEEK 3 14
| 2.31 | get data connent function encyclopedia | Na | 2022-11-14 | 2022-11-14 | 1 | 100% | bar: WEEK 3 14
| 2.32 | get data connent function list Content | Na | 2022-11-15 | 2022-11-16 | 1 | 100% | bar: WEEK 3 15
| 2.33 | get data connent function preview | Na | 2022-11-15 | 2022-11-16 | 1 | 70% | bar: WEEK 3 15 to WEEK 3 16
| 2.34 | get data connent function tag | Na | 2022-11-15 | 2022-11-16 | 1 | 90% | bar: WEEK 3 15 to WEEK 3 16
| 2.35 | get data connent function breadcrumbs | Na | 2022-11-15 | 2022-11-16 | 1 | 50% | bar: WEEK 3 15 to WEEK 3 16
| 2.36 | get data connent function slug | Na | 2022-11-15 | 2022-11-16 | 1 | 50% | bar: WEEK 3 15 to WEEK 3 16
| 2.37 | crawler knowledge support OG | Na | 2022-11-16 | 2022-11-17 | 2 | 10% | bar: WEEK 3 15 to WEEK 3 16
3. System Test & Fix bug
| 3.1 | Home Page | All | 2022-11-21 | 2022-11-21 | 1 | 0% | bar: WEEK 4 21
| 3.2 | Blog detail | All | 2022-11-22 | 2022-11-22 | 1 | 0% | bar: WEEK 4 22
| 3.3 | Category Level 1 | All | 2022-11-23 | 2022-11-24 | 2 | 0% | bar: WEEK 4 23 to WEEK 4 24
| 3.4 | Category Level 2 | All | 2022-11-23 | 2022-11-24 | 2 | 0% | bar: WEEK 4 23 to WEEK 4 24
| 3.5 | Category Level 3 | All | 2022-11-23 | 2022-11-24 | 2 | 0% | bar: WEEK 4 23 to WEEK 4 24
| 3.6 | Search result | All | 2022-11-24 | 2022-11-24 | 1 | 0% | bar: WEEK 4 24
4. UX/UI Test & Fix bug
| 4.1 | Home Page | All | 2022-11-25 | 2022-11-25 | 1 | 0% | bar: WEEK 4 25
| 4.2 | Blog detail | All | 2022-11-28 | 2022-11-28 | 1 | 0% | bar: WEEK 5 28
| 4.3 | Category Level 1 | All | 2022-11-29 | 2022-11-30 | 2 | 0% | bar: WEEK 5 29 to WEEK 5 30
| 4.4 | Category Level 2 | All | 2022-11-29 | 2022-11-30 | 2 | 0% | bar: WEEK 5 29 to WEEK 5 30
| 4.5 | Category Level 3 | All | 2022-11-29 | 2022-11-30 | 2 | 0% | bar: WEEK 5 29 to WEEK 5 30
| 4.6 | Search result | All | 2022-11-30 | 2022-11-30 | 1 | 0% | bar: WEEK 5 30
5. Optimization SEO
| 5.1 | Gennerate Sitemap | All | 2022-11-25 | 2022-11-28 | 2 | 0% | bar: WEEK 4 25 to WEEK 5 28
| 5.2 | Fix Google Search Console | All | 2022-12-09 | 2022-12-13 | 3 | 0% | bar: WEEK 1 9 to WEEK 2 13
6. Launch Website
| 6.1 | Soft launch and send internal team review | All | 2022-12-01 | 2022-12-01 | 1 | 0% | bar: WEEK 5 1
| 6.2 | Send web to Biz review | All | 2022-12-01 | 2022-12-01 | 1 | 0% | bar: WEEK 5 1
| 6.3 | Receive feedback reivew from Biz and Fix issue | All | 2022-12-02 | 2022-12-07 | 4 | 0% | bar: WEEK 5 2; WEEK 1 6 to WEEK 1 7
| 6.4 | Official launch | All | 2022-12-08 | 2022-12-08 | 1 | 0% | bar: WEEK 1 8
Formulas:
DURATION ( * 25 Days ) = NETWORKDAYS.INTL([START DATE (m/d/y)],[DUE DATE (m/d/y)],1)

## report
04-08 ยอดหายไป 50 % | upv

## Task status update 20-05-2022 (hidden)
No. | Title | Page | Owner | Ref Slide | Remark
1 | เตรียมตัว TCAS เมื่อกด See more แต่ละ Category ต้องทำหน้ารองรับหมวดนั้นๆ ในหน้าหลักเว็บไซต์ TCAS (ทำ Design , API ใหม่, แก้เว็บไซต์) | TCAS | TRUE | 14 | Phase 2
3 | แก้การแสดงข้อมูล Display Name | Member Profile | TRUE | 34 | Phase 2
4 | ค้นหาข่าวค่าย ทำปุ่ม View All และมีหน้ารับการกดแสดงแบบลิสต์ คล้ายบทความข่าวรับตรง | TCAS | Vendors | 37 | Phase 2
5 | หน้า Plook TCAS กดไปที่แท็บ “เด็กซิ่ว” แล้ว หน้าจอไม่ Auto Slide แท็บมาให้หลังจากกดเสร็จแล้ว | TCAS | Vendors | 174 | Bug จาก Phase 1 ที่ยังไม่ได้แก้
6 | คลิกเลือก “สถาบันการศึกษาทั้งหมด” แต่ในช่อง Default “สถาบันการศึกษา” ทำให้ผู้ใช้เข้่าใจผิด ว่าไม่ได้เลือกข้อมูล เคสนี้เป็นกับ Dropdown รูปแบบ, สถาบันการศึกษา, กลุ่มคณะ, ระดับการศึกษา, สถานะการเปิดรับสมัคร | TCAS | Vendors | 177.4 | Bug จาก Phase 1 ที่ยังไม่ได้แก้
7 | หน้า Plook TCAS กรณีชื่อบทความยาว 3 บรรทัด และบทความนั้นม icon เครียริ่งเฮ้าส์ รูป icon จะโดนตัด เป็นเฉพาะใน Android | TCAS | Vendors | 178.2 | แก้จาก Phase 1 แต่ยังเทสไม่ผ่าน
8 | หน้า Plook TCAS ส่วนของข่าวรับตรง ไม่แสดงกรอบครอบ icon มหาวิทยาลัยเหมือนในดีไซต์ ทั้ง Android และ iOS | TCAS | Vendors | 178.3 | แก้จาก Phase 1 แต่ยังเทสไม่ผ่าน
9 | ใน Page Level 3 ทั้งหมด ทั้งที่เป็นหน้า Native page และ Webview ต้องมีปุ่ม < และ x ทำทั้ง iOS , Android กดจากหน้าไหน เมื่อกด X ปิด ก็ให้กลับไปที่หน้านั้น | TCAS | Vendors | 180 | แก้จาก Phase 1 แต่ยังเทสไม่ผ่าน
10 | ในหน้า Favorite เลือก EXAM จะเจอขนาดรูปบทความแสดงเล็กบ้างใหญ่บ้าง ทั้งที่รูปดังกล่าวเรียกเรียก image static https://static.trueplookpanya.com/application/favorite/exam_mobile.png เคสนี้เป็นเฉพาะ iOS | Favorite | Vendors | 188 | แก้จาก Phase 1 แต่ยังเทสไม่ผ่าน
11 | - ทุกปุ่มสามารถเลื่อนตำแหน่งได้ - ปุ่มไม่สิง แยกของใครของมัน - เลือกอะไรก็แสดงกรอบแดงอันนั้น โดยตำแหน่งยังเหมือนเดิมตาม CMS ที่กำหนดไว | My Preset | Vendors | 204 | Phase 2
12 | เข้าระบบ CMS เจอปัญหา 404 Not Found กดเลือกเมนู Preset เลือก All -> Edit แล้วกด Reload browser | CMS | Vendors | 205.2 | Bug จาก Phase 1 ที่ยังไม่ได้แก้

## Copy of Timeline (hidden)
` |  | Timeline
PROJECT TITLE |  |  |  | TPPY : Application
PROJECT UPDATE |  |  |  | 2022-03-09
Mar
| WBS NUMBER | TASK TITLE | Owner | Ref. Slide no. | START DATE (m/d/y) | DUE DATE (m/d/y) | DURATION | PCT OF TASK COMPLETE | WEEK 24 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 1 | [6 empty] | WEEK 4
[9 empty] | 1 | 2 | 3 | 4 | 5 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22
| 1 | Developer : TRUE | [5 empty] | True : 50% | WEEK 1 7: วันจักรี | วันสงกรานต์ | วันสงกรานต์ | วันสงกรานต์
| 1.1 | Explore Page / ให้เรียงชื่อกลุ่มคณะ จาก ก…ฮ | Dev API | 11 | 2022-03-07 | 2022-03-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9; WEEK 1 4
| 1.2 | Plook TCAS Page / ข้อ 1, 2 | Dev API | 13 |  |  |  | 0%
| 1.3 | Plook TCAS Page ข้อ 1, 4, 5 , ใส่ลิงค์ See more | Dev API | 14 | 2022-03-07 | 2022-03-09 | 3 | 80% | bar: WEEK 2 7 to WEEK 2 9
| 1.4 | Plook TCAS Page ข้อ 1 | Dev API | 16 | 2022-03-07 | 2022-03-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9
| 1.5 | Plook TCAS Page ข้อ 2,3 | Dev API | 22 | 2022-03-07 | 2022-03-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9
| 1.6 | Plook TCAS Page ->ข่าวรับตรง ข้อ 1 | UX / UI | 23 | 2022-03-07 | 2022-03-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9
| 1.7 | Plook TCAS Page->ข่าวรับตรง ข้อ 1 | Dev API | 24 |  |  | 0 | 0%
| 1.8 | Favorite Page->ข่าวรับตรง ข้อ 2, 4 | Dev API | 26 |  |  | 0 | 0%
| 1.9 | Favorite Page-> ข้อ 1 | Dev API | 27 | 2022-03-07 | 2022-03-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9
| 1.10 | Favorite Page-> ข้อ 1 , 2 | Dev API | 28 |  |  | 0 | 0%
| 1.11 | Favorite Page-> ข้อ 1 | Dev API | 29 |  |  | 0 | 0%
| 1.12 | More ->login ข้อ 1, 2, 3, 4 | Dev API | 31 | 2022-03-07 | 2022-03-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9
| 1.13 | More ->login ข้อ 1 | Dev API | 34 |  |  | 0 | 0%
| 1.14 | Plook TCAS Page->ข่าวรับตรง ข้อ 1, 2 | Dev API | 37 | 2022-03-07 | 2022-03-09 | 3 | 100% | bar: WEEK 2 7 to WEEK 2 9
| 1.15 | Home Page ->Plook Tutor ข้อ 4 | Dev API | 44 | 2022-03-14 | 2022-03-15 | 2 | 80% | bar: WEEK 2 11 to WEEK 3 14
| 1.16 | Home Page ->Knowledge ข้อ 6 | Dev API | 46 |  |  | 0 | 0%
| 1.17 | Home Page ->Knowledge ข้อ 7 | Dev API | 47 |  |  | 0 | 0%
| 1.18 | Explore Page ข้อ 8 | Business | 49 | 2022-03-11 | 2022-03-11 | 1 | 100% | bar: WEEK 2 11
| 1.19 | Favorite Page-> ข้อ 14 | Dev API | 54 |  |  | 0 | 0%
| 1.20 | Favorite Page-> ข้อ 1 | Dev API | 56 |  |  | 0 | 0%
| 1.21 | Home Page ข้อ 1, 2, 3 | Business | 59 | 2022-03-11 | 2022-03-11 | 1 | 100% | bar: WEEK 2 11
| 1.22 | Home Page ข้อ 1, 2, 3 | Dev API | 66 |  |  | 0 | 0%
| 1.23 | Explore Page ข้อ 1 | Business | 71 | 2022-03-14 | 2022-03-14 | 1 | 100% | bar: WEEK 3 14
| 1.24 | Explore Page ข้อ 1 | Business | 72 | 2022-03-14 | 2022-03-14 | 1 | 100% | bar: WEEK 3 14
| 1.25 | Explore Page ข้อ 1 | Business | 73 | 2022-03-14 | 2022-03-14 | 1 | 100% | bar: WEEK 3 14
| 1.26 | Plook TCAS / ข่าวรับตรง ข้อ 2 | Dev API | 77 |  |  | 0 | 0%
| 1.27 | Plook TCAS / ข่าวรับตรง ข้อ 2 | Dev API | 78 |  |  | 0 | 0%
| 1.28 | ต้องเช็คใน Android | Dev API | 79 |  |  | 0 | 0%
| 1.29 | รอ Business Confirm |  | 82 |  |  | 0 | 0%
| 1.30 | Explore Page ข้อ 1 | Dev API | 83 |  |  | 0 | 0%
| 2 | Developer : Vendor | [5 empty] | Vendor : % | bar: WEEK 2 7 to WEEK 1 6
| 2.1 | Splash Screen ->แก้ชื่อ App | Dev APP | 3 | 2022-03-03 | 2022-03-18 | 12 | 0% | WEEK 3 15: Fix app; WEEK 5 28: test; WEEK 1 4: submit; WEEK 1 6: on prod |  |  |  | PR
| 2.2 | Splash Screen ->แก้ไขข้อความจาก © 2021 เป็น © 2022 | Dev APP | 4 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.3 | Home Page / ข้อ 1 | Dev APP | 6 | 2022-03-07 | 2022-03-07 | 1 | 100% | bar: WEEK 2 7
| 2.4 | Explorer Page / ข้อ 1 | Dev APP | 8 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.5 | Explorer Page / ข้อ 1 | Dev APP | 9 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.6 | Explorer Page / ข้อ 1 | Dev APP | 10 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.7 | Plook TCAS Page / ข้อ 1 | Dev APP | 11 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.8 | Home Page / ข้อ 1 | Dev APP | 12 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.9 | Plook TCAS Page / ข้อ 2 | Dev APP | 13 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.10 | Plook TCAS Page ข้อ 1, 2, 3, 4, 5 , 6 | Dev APP | 14 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.11 | Plook TCAS Page ข้อ 1 | Dev APP | 15 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.12 | Plook TCAS Page ข้อ 1 | Dev APP | 17 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.13 | Plook TCAS Page ข้อ 1 | Dev APP | 18 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.14 | Plook TCAS Page ข้อ 1 | Dev APP | 19 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.15 | Plook TCAS Page ข้อ 1 | Dev APP | 20 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.16 | Plook TCAS Page ข้อ 1 | Dev APP | 21 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.17 | Plook TCAS Page ข้อ 1 | Dev APP | 22 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.18 | Plook TCAS Page ->ข่าวรับตรง ข้อ 1 | Dev APP | 23 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.19 | Plook TCAS Page->ข่าวรับตรง ข้อ 2 | Dev APP | 24 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.20 | Favorite Page->ข่าวรับตรง ข้อ 1, 3,5 | Dev APP | 26 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.21 | More ->login ข้อ 1, 2, 3, 4 | Dev APP | 31 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.22 | More ->login ข้อ 1 | Dev APP | 32 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.23 | More ->login ข้อ 1 | Dev APP | 33 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.24 | More ->login ข้อ 1 | Dev APP | 36 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.25 | Plook TCAS Page->ข่าวรับตรง ข้อ 1, 2, 3 | Dev APP | 37 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.26 | Explorer Setting Page / ข้อ 1 | Dev APP | 68 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.27 | Plook TCAS / ข่าวรับตรง ข้อ 1 | Dev APP | 77 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.28 | Plook TCAS / ข่าวรับตรง ข้อ 1 | Dev APP | 78 | 2022-03-03 | 2022-03-18 | 12 | 0%
| 2.29 | More ->login ข้อ 1 | Dev APP | 85 | 2022-03-03 | 2022-03-18 | 12 | 0%
|  | Total Duration |  |  |  |  | 368
Formulas:
DURATION = NETWORKDAYS.INTL([START DATE (m/d/y)],[DUE DATE (m/d/y)],1)

## Copy of Gantt Chart (hidden)
GANTT CHART
| PROJECT TITLE | OS2020 |  |  |  |  | COMPANY NAME | [6 empty] | TVG
| PROJECT MANAGER | - |  |  |  |  | DATE | [6 empty] | 2020-01-01
[7 empty] | JAN | [22 empty] | FEB | [19 empty] | MAR | [21 empty] | APR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE (m/d/y) | DUE DATE (m/d/y) | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  | WEEK 15 |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19
[7 empty] | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30
1 | Project Conception and Initiation | [5 empty] | WEEK 5 27: หยุดชดเชยตรุษจีน; WEEK 7 10: หยุดชดเชยมาฆบูชา; WEEK 16 6: วันจักรี; WEEK 17 13: วันสงกรานต์; WEEK 17 14: วันสงกรานต์; WEEK 17 15: วันสงกรานต์
1.1. | Research WordPress Theme & Plungin, Database, Google Ads Manager | Toang, Boom, Kung, Jit | 2019-11-29 | 2020-01-03 | 26 | 100% | bar: WEEK 1 1 to WEEK 1 3; WEEK 2 10
1.2 | Receipt Requirement from Businesses Team | Toang, Boom, Kung, Jit | 2020-01-06 | 2020-01-06 | 1 | 100% | bar: WEEK 2 6; WEEK 2 10
1.3 | Study VidoRev - Video WordPress Theme | Toang, Boom, Kung | 2020-01-07 | 2020-01-10 | 4 | 100% | bar: WEEK 2 7 to WEEK 2 10
1.4 | Study Ads Manager for WordPress | Toang, Boom, Kung | 2020-01-10 | 2020-01-17 | 6 | 100% | bar: WEEK 2 10 to WEEK 3 17
1.5 | Setup Server Dev , Stage , Secuerity | Kook,Toang | 2020-01-15 | 2020-01-17 | 3 | 100% | bar: WEEK 2 10; WEEK 3 15 to WEEK 3 17
1.6 | Study description of the database on WordPress | Hi, Jit | 2020-01-14 | 2020-01-16 | 3 | 100% | bar: WEEK 2 10; WEEK 3 14 to WEEK 3 16
1.6 | Setup Google Ads Manager Example | Toang, Boom, Kung | 2020-01-17 | 2020-01-22 | 4 | 100% | bar: WEEK 2 10; WEEK 3 17 to WEEK 4 22
1.7 | Study Visualize WordPress System | Bell | 2020-01-20 | 2020-01-23 | 4 | 100% | bar: WEEK 2 10; WEEK 4 20 to WEEK 4 23
2 | Project Design [ Ads ] *Ref after Meeting on 01/22/2020 | bar: WEEK 1 1 to WEEK 4 24; WEEK 5 28 to WEEK 6 7; WEEK 7 11 to WEEK 15 3; WEEK 17 16 to WEEK 19 30
2.1 | Billboard1 | Toang, Boom, Kung | 2020-01-23 | 2020-01-29 | 4 | 100% | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 5 29
2.2 | Billboard2 | Toang, Boom, Kung | 2020-01-23 | 2020-01-29 | 4 | 100% | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 5 29
2.3 | App Install on Mobile | Toang, Boom, Kung | 2020-01-23 | 2020-01-29 | 4 | 100% | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 5 29
2.4 | Majorboard | Toang, Boom, Kung | 2020-01-23 | 2020-01-29 | 4 | 100% | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 5 29
2.5 | Big Banner | Toang, Boom, Kung | 2020-01-23 | 2020-01-29 | 4 | 100% | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 5 29
3 | Project Design [ Layout] *Ref after Meeting on 01/22/2020 | bar: WEEK 1 1 to WEEK 4 24; WEEK 5 28 to WEEK 6 7; WEEK 7 11 to WEEK 15 3; WEEK 17 16 to WEEK 19 30
3.1 | Home | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.2 | Mobile | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.3 | PC Game | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.4 | Console Game | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.5 | Movie | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.6 | Anime | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.7 | Entertainment | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.8 | Content View and Video View | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.10 | Content Listing Click by Category name | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.11 | Content Listing Click by Tags | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.12 | Content Listing by Search keyword | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.13 | Content Listing Click by Author name | Toang, Boom, Kung | 2020-01-06 | 2020-01-30 | 18 | 90% | bar: WEEK 2 6 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
3.14 | Anime Season | Toang, Boom, Kung | 2020-01-29 | 2020-01-31 | 3 | 70% | bar: WEEK 2 10; WEEK 5 29 to WEEK 5 31
3.15 | About ,Contact Us, Job design on one page | Toang, Boom, Kung |  |  | 0 | bar: WEEK 2 10
4 | Project Develop [ Remigration ] | bar: WEEK 1 1 to WEEK 4 24; WEEK 5 28 to WEEK 6 7; WEEK 7 11 to WEEK 15 3; WEEK 17 16 to WEEK 19 30
4.1 | Set Category for Content Version WP | Jit, Hi | 2020-01-23 | 2020-01-30 | 5 | 100% | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 5 30
4.2 | Set Condition for Display Content on Frontend | jit | 2020-01-23 | 2020-02-04 | 8 | 10% | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 6 4
| Home Page | Jit | 2020-01-23 | 2020-01-30 | 5 | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 6 4
| Mobile Game , PC Game, Console Game Page | Jit | 2020-01-31 | 2020-01-31 | 1 | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 6 4
| Movie, Anime, Entertainment Page | Jit | 2020-02-03 | 2020-02-04 | 2 | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 6 4
| Content View (Ariticle+Video) Page | Jit | 2020-02-04 | 2020-02-04 | 1 | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 6 4
| Content Listing Click by Category, Tags, Author ,Search keyword Page | Jit | 2020-02-04 | 2020-02-04 | 1 | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 6 4
| Other Page( Anime Season, Header, Footer) | Jit | 2020-02-04 | 2020-02-04 | 1 | bar: WEEK 2 10; WEEK 4 23 to WEEK 4 24; WEEK 5 28 to WEEK 6 4
4.3 | Mapping Category 2019 to 2020 | Hi, Bell | 2020-01-30 | 2020-02-04 | 4 | 50% | bar: WEEK 2 10; WEEK 5 30 to WEEK 6 4
Review OS Category | bar: WEEK 2 10; WEEK 5 30 to WEEK 6 4
Mapping 2020 Category with Existing Category | bar: WEEK 2 10; WEEK 5 30 to WEEK 6 4
Prepare Scripts for 2020 Category | bar: WEEK 2 10; WEEK 5 30 to WEEK 6 4
Import 2020 Category | bar: WEEK 2 10; WEEK 5 30 to WEEK 6 4
4.4 | Remigration User | Hi, Bell | 2020-01-24 | 2020-01-28 | 2 | 80% | bar: WEEK 2 10; WEEK 4 24; WEEK 5 28
Selected users & query | bar: WEEK 2 10; WEEK 4 24; WEEK 5 28
Prepare CSV for Import | bar: WEEK 2 10; WEEK 4 24; WEEK 5 28
Import users to WP | bar: WEEK 2 10
4.5 | Remigration Content [For testing template only] | Hi, Bell |  |  | 0 | 3 | bar: WEEK 2 10
| Sampling content data [all type, status & categories) |  |  |  | 0 | bar: WEEK 2 10
| Update No.Of.Views of each content |  |  |  | 0 | bar: WEEK 2 10
| Mapping category to Content |  |  |  | 0 | bar: WEEK 2 10
| Thumbnail Task |  |  |  | 0 | bar: WEEK 2 10
| Prepare scripts for 2020 Content |  |  |  | 0 | bar: WEEK 2 10
| Import 2020 Content |  |  |  | 0 | bar: WEEK 2 10
| Testing |  |  |  | 0 | 1 | bar: WEEK 2 10
4.6 | Remigration Content [For Production] |  |  |  | 0 | 5 | bar: WEEK 2 10
| Sampling content data [all type, status & categories) |  |  |  | 0 | bar: WEEK 2 10
| Update No.Of.Views of each content |  |  |  | 0 | bar: WEEK 2 10
| Mapping category to Content |  |  |  | 0 | bar: WEEK 2 10
| Thumbnail Task |  |  |  | 0 | bar: WEEK 2 10
| Prepare scripts for 2020 Content |  |  |  | 0 | bar: WEEK 2 10
| Import 2020 Content |  |  |  | 0 | bar: WEEK 2 10
4.x | Register Media |  |  |  | 0 | bar: WEEK 2 10
4.x | Remigration Content type Article |  |  |  | 0 | bar: WEEK 2 10
4.x | Remigration Content type Video |  |  |  | 0 | bar: WEEK 2 10
4.x | Remigration Thumbnail |  |  |  | 0 | bar: WEEK 2 10
| Mapping URL 2019 TO 2020 |  |  |  | 0 | bar: WEEK 2 10
| *** Do we have to create cut-off process plan? |  |  |  | 0 | bar: WEEK 2 10
0 | bar: WEEK 2 10
6 | Project Engineer [ Server] | bar: WEEK 1 1 to WEEK 4 24; WEEK 5 28 to WEEK 6 7; WEEK 7 11 to WEEK 15 3; WEEK 17 16 to WEEK 19 30
6.1 | Database | Kook, Max |  |  | 0 | 0% | bar: WEEK 2 10
6.2 | Prepair space for image | Kook, Max |  |  | 0 | 0% | bar: WEEK 2 10
0 | bar: WEEK 2 10
7 | Project Test / Performance / Monitoring | bar: WEEK 1 1 to WEEK 4 24; WEEK 5 28 to WEEK 6 7; WEEK 7 11 to WEEK 15 3; WEEK 17 16 to WEEK 19 30
7.1 |  |  |  |  | 0 | 0% | bar: WEEK 2 10
7.2 | bar: WEEK 2 10
Formulas:
DURATION = NETWORKDAYS.INTL([START DATE (m/d/y)],[DUE DATE (m/d/y)],1)
DURATION = NETWORKDAYS.INTL([START DATE (m/d/y)],[DUE DATE (m/d/y)],1)-1

## Example (hidden)
GANTT CHART
| PROJECT TITLE | OS2020 |  |  |  |  | COMPANY NAME | [8 empty] | TVG
| PROJECT MANAGER | [5 empty] | DATE | [8 empty] | 2020-01-20
[7 empty] | JAN | [14 empty] | FEB | [14 empty] | MAR | [14 empty] | APR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2018-03-12 | 2018-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | Kylie R | 2018-03-15 | 2018-03-16 | 1 | 100% | bar: WEEK 2 W
1.2 | Research | Pete S | 2018-03-15 | 2018-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Projections | Steve L | 2018-03-16 | 2018-03-22 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Stakeholders | Allen W | 2018-03-18 | 2018-03-22 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Guidelines | Malik M | 2018-03-19 | 2018-03-22 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation | Malik M | 2018-03-23 | 2018-03-23 | 0 | 50% | bar: WEEK 3 F
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | Budget | Allen W | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Communication Plan | Malik M |  |  | 0 | 0%
2.4 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Pete S |  |  | 0 | 0%
3.2 | KPIs | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%